## APRIL
April 2022 NACHC Issues & Ideas Update
Issue Number | Description | Resolution | Status | Notes
KI197404 | The Practice Preference General option “Set process date for encounter rate SIM..” does not work for secondary Payers. | 6.2021.1 PT78 5.9.2020.1 PT54 5.9.3 PT85 5.9.2 PT98 | Resolved | Must be using the holding tank and not manually enter process dates, for the fix to work as designed.
Idea Number | Description | Resolution | Status | Notes

## Known Issues
Known Issue # | Summary / Description | DEV Update | Steps to Recreate | Workaround | Reported By
KI141065 | The text “ABN_. actText” shows in the clinical tasking description box instead of the description in EHR provider inbox. | Non- Critical defect / Currently no planned release version assigned | Open EHR Go to File – System/Practice template Click on System tab and select Configuration Home template From the left navigation Click on NGKBM Config Scroll down to My Plan and check the checkbox for “Launch My Custom Plan (ord_my_custom_plan) Save and close the NGKBM Config template. Now open a new encounter and open Intake template Select specialty as family Practice and Visit Type as office visit Click on My Plan blue active text link My Custom Plan template pop-up opens up Add an Assessment Scroll down to Order Option section Select Lab Orders and any lab from the grid Hit Add Then in the Pending Orders grid, highlight the lab and hit the Place Order button Then scroll down to the Manage Orders section - Orders Highlight the lab you just ordered Click on Save & Task button Select a recipient from the Recipients list and add it to the Task Recipients list and click ok Save and close My Custom Plan Template Now, go to Inbox of the task recipient and open the task Notice that “{ABN_.actText }shows in the clinical tasking description instead of the task description. | N/A | Valley Health Team
KI141043 | Orders placed from the My Custom Plan template have the Reason/comment “My Custom Plan” on the order management pop-up templates | Non- Critical defect / Currently no planned release version assigned | Open Ngkbm Config & Ensure “Launch My Custom Plan” is selected….. | N/A | Valley Health Team
KI140970 | On the Save & Close button, there is an orphaned Assign Field Value trigger on the office_diagnostics template | Non- Critical defect / Currently no planned release version assigned | Open Template Editor Open office_diagnostics Scroll down to the Save & Close button Open the triggers window for the button Notice that there is an AFV trigger with a guid in the parameter Double click the trigger Click the ellipsis Notice that it doesn't assign any values | Workaround listed on KI | Valley Health Team
KI133634 | When using the in-article link to switch Patient Education from English to Spanish, the "Save to Encounter" feature will still save as English | Non- Critical defect / Currently no planned release version assigned | Open Patient Create a new encounter Go to File – Patient Education Enter a Search Criteria – Like Ear Ache Select the document you want – then select Spanish for the language on the document selected Then click on add to cart Then save to encounter When you open the patient education article in the encounter, it will show in English and not Spanish like you selected it. | Workaround listed on KI | El Rio CHC
KI132377 | Timeframe information does not get uploaded to order table when ordering labs from Other Labs template | Non- Critical defect / Currently no planned release version assigned | Start a new encounter Open *SOAP with Specialty: Family Practice and Visit Type: Office Visit Navigate to Labs tab Add a timeframe, select a lab, click Place Order The order will populate in the below grid with a time frame From the top of the template click on the “Other Tests” link Place a lab order from the pop up that opens, notice no time frame is available Click Place Order, the pop up closes and the order appears on the Lab Master’s data grid without a time frame. | N/A | Valley Health Team
KI105341 | The Finalize – OPH template does not contain the same master document generation options as the other Finalize templates. | Non- Critical defect / Currently no planned release version assigned | In EHR go to File > System / Practice Template > Practice > Ngkbm doc config 2. Under Practice Level Configurations check the “Enable auto-generating visit documents on Submit Code” | Workaround listed on KI | Valley Health Team
KI196125 | CCDs not parsing correctly in Custom View affecting procedures, problems and results portions of document. | Critical / Currently no planned release version assigned | Receive CCDA. Open NextGen Electronic Health Records (EHR) Load a patient that has a CCD Document Click on the Categories tab from the History Toolbar Click on the appropriate category containing the CCDA (example: HIE Documents) and double click the CCD document to open the CDA Viewer A tab will open up with the CDA Viewer, the tab is labeled with the date/timestamp and document name. Review the procedure section will have XML tags/guids in human readable section instead of the procedure description. | View in CCDA in Full View | OSIS / Heartland

## Ideas
ID | Title | Idea Body | Status | Created Date | Created By | Account Name | Vote Total
IDEA-9195 | NGShare Appointment Confirmation | We are not able to utilize the NGShare due to the fact that a specialist is not able to sent back the patient's scheduled appointment date and time. We would like this built into the share (direct messaging) infrastrucure. #NACHC | Awaiting Client Voting | 2018-12-18 | Sean Folweiler | Valley Health Team | 60
IDEA-8664 | Maintain Window Size of Clinical Reconciliation Module | The Clinical Reconciliation module is unusable in its current default size when opened as a popup (via View->Clinical Reconciliation or during immunization reconciliation). When a user opens the Clinical Reconciliation module they have to make the window bigger in order to work with it. And currently users have to resize the window every time they open the CR module. This idea is for the application to remember, by user, the last size of the Clinical Reconciliation module and to open the window to that size next time. Similar functionality currently exists for the EHR Workflow/Inbox/PAQ window. NACHC | On the Roadmap | 2018-09-27 | Cordt Byrne | One World Community Health Centers, Inc | 240
IDEA-7937 | PRAPARE tool | We would like to have the percent of poverty display on the PRAPARE template #NACHC | On the Roadmap | 2018-06-12 | Jess Libby | (YOR) York County Community Health | 160
IDEA-7610 | #nachc HQM Please Add Measure Summary Report for MU Modified Stage 2 2018 Program | NACHC - With the addition of the 2018 programs as of 4/27/18, immediately noticed there is not a Measure Summary Report option for MU Objectives Modified Stage 2 2018, which would be used to review performance for the Medicaid EHR Incentive Program. The Measure Summary Report format is very helpful in gauging a high-level, longitudinal view from a practice perspective, when using MU Objectives to support other quality reporting initiatives such as PCMH. Additionally, it can be beneficial to review all providers' objective performance, on a whole, throughout the configured 90-day reporting period for the incentive program. Without the Measure Summary Report format a practice would need to generate a Provider Summary NPI Report, which would only display individual provider performance in the Summary Report format used for attestation versus a user-friendly format displaying all selected providers simultaneously. Highly recommend adding this reporting option back to the MU Objectives Modified Stage 2 2018 program. | Awaiting Client Voting | 2018-05-01 | Elizabeth Sledge | Ohio Shared Information Svcs | 390
IDEA-7515 | Add Lab result and/or result value during ICS scanning | NACHC - The ability in 5.9 to link a scanned image to an order in the EHR is great. We would like to go to the next step and be able enter in the lab results, diagnostic results, etc. #NACHC Idea | Awaiting Client Voting | 2018-04-18 | Sean Folweiler | Valley Health Team | 80
IDEA-5877 | Document Mangement (ICS) Toolbar EDR | NACHC - We would like to be able to add the EDR icon to the Document Mangement (ICS) toolbar. After clicking the same sync function will occur between applications. #NACHC | Awaiting Client Voting | 2017-10-23 | Sean Folweiler | Valley Health Team | 60
IDEA-4712 | Title X Regulatory Template Update | NACHC - The Title X programs requires Sexual Orientation and Gender Identy as well as a declined option. Please add the fields to this template as a shared fields with the confidential social history fields or at least sync between the two. #NACHC #REG | Not Planned | 2017-06-28 | Sean Folweiler | Valley Health Team | 40
IDEA-3485 | Ability to Hide Test Code Favorites When Hiding from the Test Code Master | NACHC - Currently, when hiding a test code (la/b/rad) from FM Test Code master it does not hide it from any favorites lists where the test code also exists. This is very problemeatic when codes become expired and do not want providers to use them. Our current process is adding (old) to the end of the code so it can be seen and removed when coming across. We want to be able to manage test codes at a system level and not have to rely on workarounds or SQL queries to locate where test code favorites exists. Hiding the code from the test code master should allow the ability to hide from all other instances as this is the source of where it was created. #NACHC | Awaiting Client Voting | 2017-03-14 | Ryan Hensler | Lifelong Medical Care | 340
IDEA-2488 | Release Immunization Module Vaccine Schedule Updates Independent of Application Version Upgrades | NACHC - The CDC's immunization schedule is not static. The change with HPV for patients younger than 15 is just one example of a recent change. It is important for these changes to be reflected in the immunization module's calculation of vaccine status. Currently, changes to EHR immunization module's schedule are released with application upgrades/updates. This idea is for updates to the module's immunization schedule to be released as stand-alone releases, similar to the medication updates, so as to enable NextGen to release updates faster and allow clients to take them sooner. The current process of updating the immunization schedule via version releases and version hot fixes adds delays to the release date. And the fact that these updates are included in larger version upgrades or even a hot fixes is another barrier for clients to be able to get these updates into their production systems. If the immunization module's schedule was released as a separate update, similar to the current medication module updates, this would make it easier and faster for NextGen's clients. | On the Roadmap | 2016-11-10 | Cordt Byrne | One World Community Health Centers, Inc | 1260
IDEA-2459 | Add Option to Abstain from Voting on Ideas | NACHC - As an enthusiastic user of the NextGen Success Community, I don?t want a single new idea to slip by my eyes. Currently this can be done if I promote or demote every idea. Then I can see those ideas that I haven?t voted on yet. But not every idea is applicable to me / my practice; there are ideas that I don?t want to promote nor demote. And currently there is no way to mark an Idea as being viewed other than voting for or against it. This idea is to allow for a third option for Idea voting: Abstain . Combined with IDEA-0351 this would enable me to easily see all Ideas that I had not yet reviewed. Also, ideally users would be able to promote or demote previously-abstained ideas. Sourced by NACHC | Not Planned | 2016-11-04 | Cordt Byrne | One World Community Health Centers, Inc | 130
IDEA-13823 | Stop Excluding Visits based off of Diagnosis | In 2020 a decison was made to remove visits from table 5 if the patient only has "COVID-19" diagnosis on their chart. There is nothing in the UDS manaual that states to do this. We can have patients that have seen us for only covid treatment not just a vaccination or a test. We have to ensure our workflows are sufficent to not include visits that are not visits in the UDS report. When this decision was made I shared my concerns over it then and was told something would be done for 2021 yet again the tool is removing visits based off of diagnosis. This should not have to be an idea to get fixed as this is an issue. Please ensure the UDS tool is holding true to counting all encounters with the 'qualifying encounter' flag as a visit on the UDS tool. #NACHC | New | 2022-01-20 | Sean Folweiler | Valley Health Team | 60
IDEA-13796 | Launch ePM patient chart from Report Server Report | In order to ensure ultimate performace of the PROD environment for our clinical staff we force some reports to be run off of report server. It would be really helpful if clicking on a record on the report launched the patient in the ePM just like the report works when running it out of the ePM (example kept appointment no charges, unbilled charges and encounters with no charges). #NACHCIdea | New | 2022-01-10 | Sean Folweiler | Valley Health Team | 60
IDEA-13717 | Immunization Module - Filter Lot Number picklist by CPT (in addition to CVX) | This idea is to filter the "Lot #" picklist on the Vaccine Details tab by CVX and CPT . Currently the picklist is only filtered by CVX. This request is to filter the lot numbers that show up in the picklist by CPT as well as CVX. Orders ordered on the Select Vaccines tab are tied to a CVX code and a CPT code. But the dropdown of lot numbers on the Vaccine Details tab are only filtered by CVX. This is problematic for cases where one CVX is linked to multiple CPT codes, e.g. Moderna COVID vaccine. NACHC | On the Roadmap | 2021-12-06 | Cordt Byrne | One World Community Health Centers, Inc | 80
IDEA-13716 | Immunization Module - Filter Admin CPT4 picklist by CVX & CPT4 | For the COVID vaccines, we have added 10-12 administration codes to the Admin CPT4 picklist via File Maintenance -> Vaccine Admin Billing. When documenting the administration of a COVID vaccine, clinical staff have to wade through the long list to find the admin code they are looking for. Of the 12 admin codes, only two to four could possibly apply to any one order. This IDEA is to allow us to specify, in File Maintenance, the CVX & CPT (or, at least, the CVX) to which an admin code applies. Then, in the Immunization Module, on the Vaccine Details tab, the Admin CPT4 picklist would be filtered for the current CVX/CPT. This would make life easier for clinical staff and reduce the chance that they select an incorrect admin code. NACHC | Awaiting Client Voting | 2021-12-06 | Cordt Byrne | One World Community Health Centers, Inc | 60
IDEA-13658 | Interoperability Rules Engine ? Copy name between files received in a single batch | We would like to rename one document based on the name of another document received in the same batch/set. For example, we receive a C-CDA with a description of "attachment-1" and a text file that has a valuable description, e.g. "Inpatient Discharge on mm/dd/yyyy." We would like to be able to create a rule to rename the poorly named C-CDA to the meaningfully named associated text file. NACHC | Requesting Information | 2021-11-11 | Cordt Byrne | One World Community Health Centers, Inc | 270
IDEA-13657 | Interoperability Rules Engine - When renaming the document, allow use of the incoming/original document description in the new name | This request is to allow for rules to be built where the document is renamed, but the original name is part of the new name. We would like to append the document format, e.g. ?PDF? or ?C-CDA?, to the incoming document description for some documents. For example, we currently receive a batch of three or four documents. Two of the documents are named the same, e.g. "Referral Summary - ProviderName - Date." We'd like to append the format type to the description of these documents such that providers can distinguish them before opening. E.g. "Referral Summary - {ProviderName} - C-CDA" and "Referral Summary - {ProviderName} - PDF." It would be helpful if we could build a rule that references the original name when renaming a document, e.g. NewName = {OriginalName} + "PDF" NACHC | Existing Feature | 2021-11-11 | Cordt Byrne | One World Community Health Centers, Inc | 260
IDEA-13461 | UDS 6a Mapping Export | The code mapping export to excel for table 6a does not include the 'Code Range Min' and 'Code Range Max' without these columns the mapping export for 6a is almost worthless. Please add the 'Code Range Min' and 'Code Range Max' columns to the code mapping export for table 6a. #NACHC | New | 2021-09-10 | Sean Folweiler | Valley Health Team | 10
IDEA-13456 | Sort Claim Status Production Report by Encounter Location (not facility) | Currently, the location on the Claim Status Production Report is pulling the Facility Location. Upon opening a case, we were told this report is working as designed although admitting it was flawed. It should also have the option for the encounter location. The facility information for us can be the same for various encounter locations given how we bill. We need the option to sort by ENCOUNTER location. In addition, please appropriately label this field to reflect where the data is pulling from, facility vs encounter, like other NG reports. #NACHC | New | 2021-09-09 | Anne Frunk | (SST) Shasta Community Health Center | 20
IDEA-13436 | Bulk Rebill for Encounters in Billed Status | Currently if you want to do a bulk rebill, you have to manually go into each encounter and check the boxes for rebill in balance control. We do not want to regenerate claims and in some cases the claims were purposesly deleted, therefore regeneration would not work. It would be nice to run an encounters report, select the filters you need and add functionality that would allow you to select all or some for rebill right off the report. Or have the functionality to rebill encounters in the encounter lookup screen and bill without getting the error "No specified charge amounts found on the encounter to process." #NACHC | Under Review | 2021-09-02 | Anne Frunk | (SST) Shasta Community Health Center | 180
IDEA-13413 | PM Reporting on Alternate Payer for Claim Requests, Encounters and Aging | IDEA# 9365 (Please combine votes) It should be transparent to the billing department which payer generated the claim (Parent vs. Alternate) With the current functionalilty, the Alt Payer name does not show up in reports nor in the claim request window. These both display the main Payer ID, not the one on the Alternate Payer tab. It should be obvious for end-user which payer prepared a claim. This will minimize training of employees, avoid giving inaccurate information to patients, and wasting time contacting the wrong payer when following up on claim payments, etc. I would like to add that CFOs and Billing Managers want the capability to report on Alternate Payers, Aging By Alternate Payers, and Contract Library by Alternate Payers as well. Thank you. #NACHC | New | 2021-08-24 | Anne Frunk | (SST) Shasta Community Health Center | 40
IDEA-12705 | Audit execution of stored procedures via template triggers in Advanced Audit | Currently Advanced Audit does not log when database edits are made via stored procedure. When Stored Procedure triggers on templates are executed, there is nothing logged in Advanced Audit. It is impossible to tell who modified data in a patient's chart if that data was modified via a Stored Procedure trigger. That makes it difficult to research questions/issues. Assuming that it would be too difficult to track all tables and fields that are updated via stored procs, this Idea is to at least track when stored procedure triggers are fired on templates. It would be helpful to know the name of the stored procedure that was executed as well as the values for parameters. NACHC | Awaiting Client Voting | 2021-01-22 | Cordt Byrne | One World Community Health Centers, Inc | 150
IDEA-12704 | Template Export and Import Using a Command Prompt | Create the functionality such that template import and export can be executed via command line / batch file . NextGen documents can now be exported, imported, and compiled via command line functionality. This idea is to create similar functionality for templates . This functionality would make deployment of edited/updated templates much easier. It would cut out many steps that are currently in the workflow of using Template Import/Export: launching NextGen, launching Template Import/Export, verifying import options, and locating files to import. These steps add up when deploying to multiple databases (e.g. NGDemo and NGTest, or eight NGProds in our case) This functionality would also make it possible to periodically back up templates. We could write a batch file to periodically export templates to backup folders. NACHC | Awaiting Client Voting | 2021-01-22 | Cordt Byrne | One World Community Health Centers, Inc | 80
IDEA-12703 | Add ability to set patient age range for VFC eligibility reasons | When documenting immunization administration, users select the VFC eligibility reason from a picklist in the orders module. Per our state, some eligibility reasons are only valid for children, some are only valid for adults, and some are valid for patients of all ages. The problem is that users frequently select an option that is invalid for the current patient. This idea is to be able to set an age range for each eligibility reason. Then in the orders module in EHR, only picklist options that are valid for the current patient's age would display. This would make it easier for the end user to select the right code. #NACHC | Awaiting Client Voting | 2021-01-22 | Cordt Byrne | One World Community Health Centers, Inc | 480
IDEA-12386 | Active Encounter Rate Report in each Encounter Rate Library | We need a report that shows all encounter libraries, effective dates for encounter rate SIMs/rates along with all of the setups with corresponding fields for each encounter rate library. #NACHC | Awaiting Client Voting | 2020-10-19 | Anne Frunk | (SST) Shasta Community Health Center | 10
IDEA-12310 | Community Resource Referral Follow Up | #NACHC. The Community Resource functionality does not provide a location for practices to indicate if the patient received services/assistance from the outside organization. These do not appear to drop to an order table category for reporting a status. NCQA PCMH has elements that require practice to track these types of referrals and monitor effectiveness of services. It would be helpful to have additional functionality to track and document if patient received services/assistance/aid from the community resource. | On the Roadmap | 2020-09-28 | Rebecca Rudd | Ohio Shared Information Svcs | 160
IDEA-12305 | Encounter Level Reciepts | We post payments at the encounter level not account level and need a way to print reciepts for patient payments at time of check-in. The encounter bill functionality looks more like a statement and has language the charges are zero, estimate from insurance is zero, and balance due from patient is zero. Because we collect payments at time of check-in, we do not know what final charges will be yet. As an FQHC, when collecting sliding fee payments, we need a way to print something that looks more like a receipt. Also, it would be helpful if when printing the receipt it is saved in the patient record in case of audit or patient despute with person who created the payment/printed receipt. We can probably develop a form within NG but it would be helpful is something like this existed in the system. #NACHC | Under Review | 2020-09-24 | Anne Frunk | (SST) Shasta Community Health Center | 130
IDEA-12232 | Configure which if any of the Gender Identity/Sex Assigned at Birth/Current Gender appear in PIB | We should be able to configure the PIB to include none of these fields or any of these fields- Birth Sex Current Gender Gender Identity #NACHC #TGNB | Awaiting Client Voting | 2020-09-11 | Richard Clarkson | Callen-Lorde Community Health Center | 90
IDEA-12169 | New Claim Edit for Invalid Principal Diagnosis | Our managed care plans will deny claims for invalid primary diagnosis. There is currently not a claim edit for invalid primary diagnosis that would still allow the invalid dx to be submitted in subsequent positions on the claim. It would helpful if this edit was also provided with range functionality. Example - Notification from payer: Subject: Invalid Principle Diagnosis Code Rejections ? Effective 8/3/20 Claims received on and after 8/3/20 will now be rejected back to the provider of service if billed with an invalid principle diagnosis code, range V00 ? Y99. Diagnosis codes in this range are not allowed in the principle diagnosis code field, but may be billed in any other position on the claim form. #NACHC | Under Review | 2020-09-02 | Anne Frunk | (SST) Shasta Community Health Center | 160
IDEA-11988 | Family Size & Income - Required Field Functionality | It would be great if the system would "reset" the family size and income fields once the income is expired. Once a required field is filled in, it's no longer flagged red since the requirement is satisfied. Staff often look past these fields since they're no longer alerted to address them/fill them in. Income is especially important for reporting and we find that a lot of the data is old since staff forget to update these fields since it's already filled in. What would be even better is if we could choose which fields need to be readdressed at a certain time interval in Practice Preferences (i.e. every year income, privacy policy and emergency contact must be flagged again for review). Although this is ideal, since the income already has an expiration date noted, it's probaby easier/quicker to accomplish. #NACHC | Under Review | 2020-07-28 | Tameka Frank | Ohio Shared Information Svcs | 740
IDEA-11925 | UDS Virtual Visits | With the guidelines for virutal visits the same codes that are used for face to face will be used for virutal visits (99202-99205, 99212-99215) We created 99202T and 99202V to be able to differenate between telephone and virutal (synchronous visits). We would perfer the virutal mapping to be based off of SIM rather than CPT. #NACHC | New | 2020-07-13 | Sean Folweiler | Valley Health Team | 40
IDEA-11552 | UDSReporting Table 6A | A request to UDS reporting developers to include the option for Table 6A to allow running reports for individual diagnosis ? It takes a very long time for table 6A to run & if we need the data on just one or two diagnoses, it takes a long time for the report to be available. #NACHC | New | 2020-04-15 | Anu Srinivasan | Northeast Valley Health Corporation | 30

## Resolved KIs
Known Issue # | Summary | DEV Update | Steps to Recreate | Reported By
KI116892 | Creating a New Charge in the Charge Posting Window May Result in an Error Message | Known Issue Closed. Fixed in 5.9 GR | 1. Log in to EHR and create a new encounter. 2. Navigate to the Procedure Module. 3. Navigate to the Diagnosis section, 4. Enter multiple diagnosis codes and click Add. 5. Log in to Practice Management. 6. Click Charges to launch the Charge Posting window. 7. Selects a charge and click Process. 8. Click Open. 9. Navigate to the Diag section. 10. Delete any added diagnosis code and click Save. 11. Click New. 12. Add another charge and click Save. The user receives the following error message: “A change has been detected with the encounter diagnosis codes. Please cancel out of saving this charge and then re-enter it.” | El Rio Community Health Center
KI119470 | Anticoagulation Dosing, "Copy Last Dosage" does not copy the correct Dose to the Dose section of the Dosage grid. | Known Issue Closed. Fixed in the Spring Release (8.4.1) and 8.4 PT09, 8.3.11 PT12, 8.3.10, PT22 | Log onto EHR Select any patient Launch the Anticoagulation Dosing Template Specialty: Any; Visit Type: Any Under the Dosing Panel, select Coumadin for the Medication Start Date: any date Click the radio button next to Daily and select 2mg, then click Add to Grid Under Individualized Dosing, click the radio button for dose 1, then select 1mg Click on the Dose field under Tue for Tuesday, then select 1 tablet Click Calculate Click Update Create a new encounter Launch the Anticoagulation Dosing Template Specialty: Any; Visit Type: Any Under the Dosing Panel, select Coumadin for the Medication Start Date: any date Click the radio button next to “Copy Last Dosage” Note: The correct dosage is copied forward Click Add to Grid Note: The incorrect Dose is listed on the Dosage grid Click calculate Note: The total is correct Click update Click Generate Document Note: The anticoagulation_master generates the incorrect summary under Anticoagulation Therapy | El Rio Community Health Center
KI122392 | In some cases, the NextGenPortalRosettaHost service will not start upon upgrading the NextGen Communication Services to UD3. This is due to a corrupted CONFIG file in the NCS directory which will also prevent PHR/CCDAs from generating to Patient Portal, | This issue is resolved in NCS 5.8.3.128. Data cleanup available, please open a support case if needed. If you continue to experience new instances of PHR getting "stuck," please open a new case to review that issue. | In some cases, the NextGenPortalRosettaHost service will not start upon upgrading the NextGen Communication Services to UD3. This is due to a corrupted CONFIG file in the NCS directory which will also prevent PHR/CCDAs from generating to Patient Portal | NA
KI127557 | The stored procedure [ngkbm_doc_assessplan] can experience slowness on NG KBM 8.3.11 | Known Issue Closed. Released in the Spring Release(5.9.1, 8.4.1). Workaround listed. | Launch NextGen(R) Ambulatory Electronic Health Record (EHR). Click the Patient button on the menu bar. Search for any patient and press OK. Create a new encounter by pressing the New button below the Patient History tab. Press the Templates button to create a template on the new encounter. Select the IMO Template. Open Assessments on the IMO Template. | El Rio Community Health Center
KI131046 | The NCS/CCDA generation process is inserting records into the ngweb_phr_documents table at a very high rate and causing performance issues. There is currently no functionality that purges these records after an allotted amount of time. | Known Issue Closed | Steps to Recreate: 1. Upgrade NCS to UD3. 2. Ensure PHR Backfill and the Encounter CDA agent are enabled. 3. Records will be inserted into this table at a very high rate. These records will never be removed unless it is done manually. Troubleshooting Steps Taken: Connected with client and discovered the issue. Swarmed with Development on case #04445570 and a KI was requested. | Heartland CHN
KI131081 | When upgrading from 8.3.10 to 8.4 the order_.txt_receivedComment field does not get added causing an error on the Other Reports and Studies template | Known Issue Closed. Fixed in the Spring Release(5.9.1, 8.4.1) | 1. Upgrade a database from 8.3.10 to 8.4 2. Open EHR 3. Create a new encounter Specialty: Family Practice - Visit Type: Office Visit 4. Go to the SOAP template. 5. Click on Assessment 6. Add an Assessment. 7. Click on A/P Details in the top navigation bar of the popup 8. Click on the Follow Up link at the bottom of the template. 9. Document on the template and hit Place Order button 10. Click Save & Close 11. Click Order Management link in the Sub Navigation 12. Click the Other radio button 13. Highlight the order and hit Edit *** Notice the error. | Valley Health Team
KI133499 | Care Guidelines, Updates to protocols and statuses are lost when creating new encounters or refreshing/re-applying guidelines unless an order exists that matches the guideline | Known Issue Closed. Resolved in Care Guidelines 2.0 | Care Guidelines Classic Open a patient, start a new encounter. From the Templates Module, open *Intake, select a specialty and visit type. Click on the Care Guidelines link, Care Guidelines pop up opens. Click on the Risk Indicators Health Maintenance text link. Select No Risk Factors, then save and close the template. Health Maintenance protocols load for the patient. Review the guidelines and notice that a Depression Screening and Lipid Panel have populated. Highlight the Depression Screening guideline, select the Completed status, today's date, and click the Update button. Verify the guideline shows as Completed with today's date. Highlight the Lipid Panel guideline and click the Place Order button. Scroll to the Recent Orders panel, expand, and click on the Pending text. Locate and highlight the Lipid Panel order you just placed and click Edit. Mark this order as completed with today's date and save the order. Close the order template. Back on Care Guidelines, verify that the Lipid Panel guideline is updated. Save and close all open templates. Start a new encounter. From the Templates Module, open *Intake, select a specialty and visit type. Click on the Care Guidelines link, Care Guidelines pop up opens. Review the guidelines and notice the Depression Screening is no longer completed, but now shows due. Notice that the Lipid Panel is still completed. Highlight the Depression Screening guideline, select the Completed status, today's date, and click the Update button. Verify the guideline shows as Completed with today's date. Test re-applying guidelines: Click the Add/Update button to open Activate Clinical Guidelines popup. Click in Condition, select Health Maintenance and click Add. On the Risk popup, select No Risk Indicators then save and close the template. Review the Care Guidelines again and notice the Depression Screening is no longer completed again. Care Guidelines Standalone Open a patient, start a new encounter. From the Templates Module, open *Intake, select a specialty and visit type. Click on the Care Guidelines link, Care Guidelines Paged View pop up opens. Click on the Add/Update button, Activate Clinical Guidelines opens. Click in Condition, select Health Maintenance and click Add. On the Risk popup, select No Risk Indicators then save and close the template. Save and close out to Care Guidelines Paged View. Review the guidelines and notice that a Depression Screening and Lipid Panel have populated. For the Depression Screening guideline, select the Completed status and today's date. Verify the guideline shows as Completed with today's date. Locate the Lipid Panel guideline, select the checkbox, then click the Order button. Scroll to the Recent Orders panel, expand, and click on the Pending text. Locate and highlight the Lipid Panel order you just placed and click Edit. Mark this order as completed with today's date and save the order. Close the order template. Back on Care Guidelines, verify that the Lipid Panel guideline is updated. Save and close all open templates. Start a new encounter. From the Templates Module, open *Intake, select a specialty and visit type. Click on the Care Guidelines link, Care Guidelines Paged View pop up opens. Review the guidelines and notice the Depression Screening is no longer completed, but now shows due. Notice that the Lipid Panel is still completed. For the Depression Screening guideline, select the Completed status and today's date. Verify the guideline shows as Completed with today's date. Test re-applying guidelines: Click the Add/Update button to open Activate Clinical Guidelines popup. Click in Condition, select Health Maintenance and click Add. On the Risk popup, select No Risk Indicators then save and close the template. Review the Care Guidelines again and notice the Depression Screening is no longer completed again. | Valley Health Team
KI133565 | When entering Interpretation and Results on the Office Procedures – Orders template and hit submit to superbill, the procedure will bill but you get the required field txt_update error. | Known Issue Closed. Working as Designed. | 1.) New Encounter 2.) Go to *SOAP 3.) Click My Plan link 4.) Add/Enter an Assessment 5.) Click a check box under Office Procedures 6.) Click Place Order button then Click Save & Close 7.) Go to Checkout template 8.) In the Today's Orders Panel click on Office Services and your order should show up on the grid. 9.) Highlight the order in the grid and click the Edit button to launch the "Office Procedures - Orders" template pop up 10.) On the right hand side of the template, click on the completed check box. 11.) Click in Interpretation field and choose See Details from the picklist - an Update button will now appear. 12.) Add a test comment in the Result Details text box. 13.) Click the Submit to Superbill button 14.) You will get an error/alert message that the Required Field (txt_update) cannot be blank. 15.) Click ok to that message and click ok to the next message that says the template could not be saved. 16.) Click the Update button next to the Result Details text box 17.) A green checkbox appears next to a label that says "submitted" 18.) This step is optional and is not always being done: you can then select Submit to Superbill multiple times, but it should not re-submit. 19.) Save and Close the Office Procedures popup 20.) Go to the File menu and Choose Superbill 21.) The charges are sometimes displaying twice in the Procedures Grid in Superbill. | Valley Health Team
KI136245 | The stored procedure [ng_provider_approval_queue] can periodically run slowly and cause high CPU utilization on a query that checks for patient notes. | Known Issue Closed. Fixed in the Spring Release (5.9.1, 8.4.1) | Steps: Launch NextGen Electronic Health Records (EHR) Log in Open the Provider Approval Queue (PAQ) and sign in as a provider | El Rio Community Health Center
KI137470 | ePA Import processor shows errors in the Nextgen Communication Services post v5.9 upgrade. “Error updating ePA st”. | Known Issue Closed. Fixed in Spring Release (5.9.1/8.4.1) and 5.9 PT16 | Go to the server where the NCS utility is installed Open the NCS utility via the desktop icon Click ok Click on settings icon > Settings button Click next til the password window and enter password Click next til you get to 5 of 7 window Expand tree til you see ePrescribing – Retail > ePA Import Make sure box is checked and click next til the end Click Configure Client Close NCS utility Restart the services Open NCS utility View status window and click “poll now” button Errors will flash on the ePA Import processor > Error updating ePA st… | Valley Health Team
KI138609 | Using Send&Close on a tasked outgoing telephone call template will resend the task back to the initially tasked user | Confirmed Critical. The fix for this issue can be found in KBM patch 8.4 PT29, 8.4.1 PT19, 8.4.2 PT13, 8.4.3 PT5 and 8.4.4 GR. | *First make sure to enable the Attach Telephone Call template option under NGKBM Config* Open a patient Create a new encounter Open the Telephone Call template from either the Telephone button on the Patient Information Bar or from the Template picker Select a specialty if required Click Outgoing to open the Outgoing - Telephone popup template Document some information Click Send&Close Select a user to task the call to. The template closes Click Outgoing again to reopen the template Select the call in the grid that you created in step 7 Click Send&Close again. Template closes instead of prompting to task out again and sends the task to the same user as select in step 8 Log out and back into EHR as the tasked user from step 8 Open the Inbox Select the new task and accept it. The Telephone Call or Outgoing - Telephone will open depending on your NGKBM Config option If the Telephone Call template, repeat steps 9 to 11 If the Outgoing - Telephone, repeat steps 10 and 11 There is no option to select a recipient. Check the inbox and notice the task is back in the original recipient's inbox | Valley Health Team
KI138684 | Error Number 5 occurs when posting an ERA/Manual batch | Fixed in Spring Release (5.9.1/8.4.1) and 5.9 PT13 | Import ERA file or manually post payments Attempt to post batch and recieve the following error: Error Number 5 Error Description: Incorrect syntax near '-' Error Source: Nextgen.Data Called By: BatchPosting.SQL | Valley Health Team
KI138692 | Stored procedures ngkbm_doc_care_team_memb and ngkbm_udg_care_team_members are taking 30+ seconds to complete. | Known Issue Closed. Fixed in the Spring Release (8.4.1) and 8.4 PT07 | Launch Care Plan Template Generate a Patient Plan | El Rio Community Health Center
KI141035 | eyeContactLens, Unable to print the Trial contact lens prescriptions | Known Issue Closed. Working as Designed. | Log onto EHR Select any patient Create a new encounter Launch the Contact Lens Evaluation – OPH Template Scroll to the contact Lens Prescription Click on the Trial radio button Enter OD and OS information Click Print Rx 1 Note Alert: Final radio button must be selected in order to generate prescription | Valley Health Team
KI141041 | The Search box on the My Custom Plan template does not hide/show if the Locations radio button is selected and users change to Order Set view, and then goes back to Show All view. | Known Issue Closed. Released in the Fall Release(8.4.2 GR) | File > System/Practice Templates > Practice Tab > All > Open NGKBM Config; Scroll down to Orders/Plans; Make sure Launch My Custom Plan is checked off; Open *Intake; Select Specialty/Visit Type (Ex. Family Practice/Office Visit); Open *Soap; Scroll down to Assessment/Plan panel; Select Assessments; Add an Assessment; Click My Plan; Select Assessment; Select Referrals under Order Options; The defaulted radio button options for “View” is Providers and for “Show” is All; Click the Order Set radio button; Click the All radio button; Notice that the Search option can be seen; Select the Locations radio button; Select the Order Set radio button; Select the All radio button; Notice that the Search option is now hidden. | Valley Health Team
KI141070 | Telephone call template settings in "NGKBM Config Template." | Support has script available which will reestablish the xref record link in the triggers table. Issue is fixed and not reproducible in 8.4.5 versions and above. | Open EHR Go to File – System/Practice templates Select all Click on *Configuration Home Click on the NGKBM_config from the left Nav Scroll down to the Telephone Call Tasking Select a Default Tasking Category – example Telephone Call from the picklist Then Save and close the template Then click on the Inbox icon If you don’t have Telephone Call category for Clinical Tasking, you will need to add it Click on the Star by Clinical Tasking – Setup Filters Click the Add button under the filter name section – put Telephone Call for the filter name and check the box for Telephone call for the category name the hit OK Open a patient and create a new encounter Go to the template module and select Telephone Call template Click on Forms/Records Enter Call information and Communication information Then Click Send &Close Task Recipients popup appears, hit OK so you get the task Then answer Yes to the Add New Task Popup Now go to the Inbox and look under the Telephone Call task and the task will not show. ***It will show under All Tasks with no category assigned to it | Valley Health Team
KI143150 | Switching between practices when working with shared demographic template fields can cause missing or incorrect patient data. | Known Issue Closed. Fixed in the Spring Release (5.9.1, 8.4.1) and 5.9 PT13 | Clear the template cache Open a patient Create a new encounter Open *SOAP Select a specialty and visit type (FP/OV) Click Standing orders Order an X-ray test by selecting an order from the top grid, adding a diagnosis code (using the Add or Update Assessment button), and clicking Place Order Select the order in the Today's Order grid and click Edit Check both Received and Completed Click Quick Findings to open Ortho Xray Dictation Document some information and use Save & Close. Notice the quick findings show in the Result Details field Change practices Repeat steps 2-11 but now notice that quick findings do not show in Result Details field Please note that this defect affects multiple workflows, and your workflow may not be known at the time of this writing. 1. Documenting results on ort_xray_dictation (above) 2. Adding records to the OB_ProblemList Records may appear to go missing, or may be linked to the wrong pregnancy number. 3. Patient Demographics shows pharmacy data from another practice. More information under the duplicate KI 140907 4. The Disease/Disorder and Snomed code fields on "Manage Past Medical/Surgical History" do not populate for some practices. More information under the duplicate KI138665. | El Rio Community Health Center
KI143177 | When completing any test on the Office Services template, the test will not show completed in the Orders Module | KI closed. Determined to be working as designed and the known issue record is being closed, for the following reason: Orders Module was not designed to update based on a standing order. | Open patient Create New encounter Open the *intake template – Specialty – Family Practice Visit Type – Office Visit Select Standing Orders Sub Nav Select Urinalysis for the Orders grid Add a Diagnosis Go to the Results section and click on the Detail button Document the results on the Urine Dipstick popup Then Place the order The Today’s Order grid will show the order completed and show the results Click on the Labs/Radiology Order Processing Active text below grid Submit the order to the orders module When you open the Orders Module – The order is showing Ordered and not Completed | Valley Health Team
KI144262 | The Inbox button on the Top Toolbar will not launch the PAQ tab. It will launch any other last tab selected within the Inbox instead. | Known Issue Closed. Working as Designed. | 1. Login to EHR. 2.Click on the Inbox. The Inbox will launch. 3. Select the PAQ tab. 4. Close the Inbox. 5. Click on the Inbox button. the Clinical tasking tab will launch instead of the PAQ, since Clinical tasking is the ilast non-PAQ tab used. | Valley Health Team
KI144297 | When patients open documents on the nextmd website, the patient portal document history in EHR displays the following: Document was sent to NextGen Patient Portal by NextMD Services. | Known Issue Closed. Working as Designed. | 1. Log into EHR with a patient portal enrollee 2. Create a new encounter 3. Open the Documents Module and generate any document 4. Save the document to the patient’s chart 5. Right click the document 6. Select Send to Patient Portal 7. Click Send 8. Click OK on Patient Portal Document Export window 9. Right Click the document 10. Select Patient Portal History Details 11. Verify there is one entry showing the document sent by the user 12. Access nextmd.com as the patient and open the document 13. Wait a couple minutes for document history to update 14. Right Click the document 15. Select Patient Portal History 16. Verify the patient portal document history displays the following: Document was sent to NextGen Patient Portal by NextMD Services. | Heartland CHN
KI144357 | The Service Item (SIM) being displayed in the Admin CPT4 field in the Update Immunization Order window in the Orders Module may be incorrect and differ from what was billed. | Critical defect / Fixed in June Patch Releases | Available in KI Details | One World
KI144455 | ord_my_custom_plan, The Orders Grid on the My Custom Plan Template displays too many orders to be functional | Known Issue Closed. Working as Designed. | Log onto EHR Select any patient Click New to start a new encounter Launch the Intake Template Specialty: Family Practice; Visit Type: Office Visit Click on the SOAP tab Under the Assessment/Plan panel, click on Assessments Click on the Add Common Assessment active link Select any diagnosis from the Common Assessment template, then click Save & Close Click on the Labs Tab Click on the diagnosis from the Diagnosis box selected on step 9, then select any three tests Click Place Order Click Save & Close On the SOAP template, click on the Order Management sub nav Under the Order Management Template, ensure that the All Orders Radio button is selected Click on the column header “Ordered” to sort by date Click on one order created during the encounter, then click Edit On the “All Order Management” template, click the box next to Received, click save, then close Click on the next order, then click Edit On the “All Order Management” template, click the box next to Completed, click save, then close Click on the last order, then click Edit On the “All Order Management” template, click the box next to Canceled, click save, then close (cancelled is spelled incorrectly on this template, but it is not related to this issue) Click on the SOAP Tab Click on the “My Plan” subnav View the orders in the Orders grid (Note: There are cancelled, completed, and deleted orders in the grid) Create a new encounter Launch the Intake Template Specialty: Family Practice; Visit Type: Office Visit Click on the SOAP tab Click on the “My Plan” subnav View the orders in the Orders grid (Note: There are orders in the grid not from the current encounter) | Valley Health Team
KI144473 | UDS - When exporting to excel, table number is being cut off in the file name. For example, instead of 6A it shows just A and the description. | Resolved in the UDS Reporting Console 2021 Release (5.0.0.0) | Export to Excel | Valley Health Team
KI144746 | Contact Lens Evaluation - OPH (eyecontactlens) template missing key menu and functional items | Known Issue Closed. Working as Designed. | Open Template editor 1. Open template eyecontactlens | Valley Health Team
KI150051 | Getting the message “A change has been detected with the encounter diagnosis codes. Please cancel out of saving this charge and the re-enter it” after deleting a diagnosis on a charge and then trying to add another. | Known Issue Closed. Fixed in Spring Release (5.9.1/8.4.1) and 5.9 Patch 20 | 1.Create an encounter. 2.Add one charge with two diagnosis codes and then exit out of charge entry. 3.Go back to charge entry. 4.Open the charge and clear out the second diagnosis code and hit save. 5.Open the charge again and add a new diagnosis code in the second line. 6. Hit save. 7. You then get the change has been detected message. | El Rio Community Health Center
KI166574 | Many sections missing in My Chart when subsequent PHR requests are generated (i.e.)Medications, allergies, etc. | Confirmed Critical. Defect released in 4.1.0. There are other similar defects related to aggregation issues in portal as well if clients feel they may still be experiencing this. Planned Release Version of 4.1.0. [KI CLOSED] | N/A | NA
KI174207 | In the new 5.9.1 NCS versions, Export Message Processor Category 1 will fail on NGENROLL messages keeping others behind from processing | Resolved in 5.9.3, 5.9.2 PT 16 5.9.1 PT 33 | N/A | NA
KI174207 | In the new 5.9.1 NCS versions, Export Message Processor Category 1 will fail on NGENROLL messages keeping others behind from processing | 08/13/19 Tentative Patch date listed | N/A | NA
KI174381 | The vaccine schedule for HPV (CVX 165/CPT 90651) in the Immunization Module is still calculating 16 weeks between the 2nd and 3rd dose. | Confirmed Critical. 09/10 patches released. Known Issue Closed. | Access the Application Launcher Select ‘Enterprise EHR’ from the Application Launcher menu Log into EHR using your NextGen credentials Select the ‘Patient’ icon in the top toolbar to open the Patient Look up window Search for a patient over the age of 15 and does not have any HPV vaccines in their chart Double click on the record to open the patient in EHR Select ‘New’ on the Patient History Toolbar to create a new encounter Select the ‘Test Tubes’ icon to access the Orders Module Select the ‘Immunizations’ tab Select the ‘Historical’ button to access the ‘Past Vaccines Entry Form’ window Click the ‘Search’ button in the upper right corner of the ‘Past Vaccines Entry Form’ window Type ‘165’ in the CVX code field and click ‘Find’ Mark the box for vaccine CVX 165/CPT 90651 Click ‘Ok’ to add the vaccine and close the ‘Search Vaccines’ window On the first row enter ‘03/17/2018’ in the date field and select ‘Other Provider’ from the Source drop down box Begin a new row and enter ‘06/19/2018’ in the date field and select ‘Other Provider’ from the Source drop down box Click ‘Save & Close’ to close the ‘Past Vaccines Entry Form’ window The next due date in the Status column for HPV is 10/19/2018. The interval between 06/19/2018 and 10/19/2018 is 16 weeks. The current recommendation is 12 weeks. | Heartland CHN
KI174710 | Password reset does not work for patient without authoritative email | Thank you for using NextGen Healthcare Support. This issue has been fixed in PP 2.7.1 Should you need further assistance or feel this known issue record has been closed in error, please contact our Support team at 215-657-4373. | Patients receiving error message with password recovery link | NA
KI174919 | Patients are unable to create a new password during the verification process. They are receiving the message stating, “Please enter your correct password. | Thank you for using NextGen Healthcare Support. This issue has been fixed in PP 2.7.1 Should you need further assistance or feel this known issue record has been closed in error, please contact our Support team at 215-657-4373. | Patient unable to create a new password during the verification process. They are receiving the message stating "Please enter your correct password" | NA
KI177453 | Patient portal messages re-assigned to a routing group that includes a taskgroup cannot be opened. Receives error: When Address Type is Patient or Online Identity, the Address ID must be a GUID. | Confirmed Critical. Target Patch Release scheduled for 3/10/2020. | N/A | N/A
KI181560 | Measure Goal Settings > Default Goals are incorrect for '2019 Medicaid PI Stage 3' Program measures | Resolved in 5.10 HQM | 1) From HQM Portal > Config tab, click 'Measure Goal Setting' to launch page and choose '2019 Medicaid PI Stage 3' Program to load its default/custom goals. 2) For 'Coordination of Care' measures, you will see the defaults are as follows: Coordination of Care - Patient Generated Data: 5% Coordination of Care - VDT - 10% Coordination of Care - Secure Messaging: 25% 'Patient Electronic Access - Patient Education' should default to 50%. Note: All 3 'Coordination of Care' measures should be defaulted to a goal of 5%, and 'Patient Electronic Access - Patient Education' should default to 35% | N/A
KI182597 | The 2019 PI Secure Messaging measure may show extremely high numerator counts. | Resolved in 5.10 HQM | 1. Generate a Summary Report for '2019 Medicaid PI Stage 3' Program's 'Coordination of Care - Secure Messaging' measure. 2. Note the Numerator count may be extremely for this measure. | N/A
KI183589 | Encounter CDA agent is creating records with the following error: “NextGen.Data.SmartDBException: Conversion failed when converting from a character string to uniqueidentifier” | November 2019 NCS Rosetta Released for NCS part. | N/A | N/A
KI193840 | When using the Export All button to export the All Mappings report, the 6A codes do not appear on the spreadsheet. | Resolved in the UDS Reporting Console 2021 Release (5.0.0.0) | 1. Open UDS Reporting Console 2. Click on Code Mapping Icon 3. Click on Export All Mappings button The 6A tab will be blank. | Valley Health Team
KI194874 | The 2020 evaluation for CMS 165 may not appropriately evaluate "at home" measurements. | Confirmed Critical [MU] Tenative Planned Release Version of 7.0.2 HQM [Released 5/28/2020] | N/A at this time, as the data extraction is a back end process. | OSIS
KI57594 | Supervising provider ID is not saved when renewing a medication. This will cause the supervising provider information not to display on the state RX Reports. | Known Issue Closed. Fixed in the Spring Release (5.9.1, 8.4.1). Workaround listed. | Open a patient in EHR 2. Create a new encounter 3. Open the medication module 4. Prescribe a medication (save all needed details) 5. Print the prescription – notice the supervising provider information is on the report. 6. Renew the medication 7. Print the prescription – notice the supervising provider information is NOT on the report | Heartland CHN
KI66637 | All referral tasks sent from the Referrals Order template are tagged as high priority instead of a normal priority. | Known Issue Closed. Working as Designed. | 1. Launch *Intake. Select any Specialty and any visit type. 2. Open Order Management template from the subnav link or left hand navigation. Click on Referrals radio button under the Order management section, then click on Add. 3. Fill in all the details under the Referrals, including specialty, diagnosis, and services requested, then click on add. 4. The Select Task Recipients MRPop up will open up. With the default priority as high. | Valley Health Team
KI74910 | Immunizations entered as historical orders are appearing in the plan orders section for today. If there are also immunizations ordered and completed that day, they will be mixed into the historical immunizations. | Known Issue Closed. Fixed in Spring Release (8.4.1) and 8.4 PT8, 8.3.11 PT11, and 8.3.10 PT22 | 1. Open A pediatric patient. Start a new encounter 2. Open *Intake, select specialty and visit type (Tested with Pediatrics, Well Child) 3. Navigate to Pediatric Immunizations from the subnav 4. Select Historical A. Enter 3-5 historical immunizations B. Save and close 5. Navigate to *SOAP 6. You will see "Orders not associated to today’s encounter" and all the immunizations you added. The Immunizations added as ‘Historical’ should not be appearing, since they were not completed by this practice and were not given on the encounter date 7. If you also order a new immunization and complete it, that immunization will be mixed into the immunizations that were added as historical. There is nothing to specify if the Immunizations are historical. | Valley Health Team
KI75503 | When attempting to prescribe a new medication or renew a medication already in the patient’s chart, the following error appears: “Error converting data type varchar to numeric”. | Known Issue Closed. Released in the Spring Release(5.9.1, 8.4.1) | 1. Access a patient’s chart in EHR that has problems documented in the Problems/Dx Module > Problem List. 2. Access SQL and update a record for this patient to set patient_problems.concept_id to a blank value (set concept_id = ‘’) 3. In EHR, access the Medication Module and attempt to prescribe a new medication or renew an existing medication. 4. The error message will appear. | Valley Health Team
KI75673 | Master IM's not showing up in PAQ right away. The PAQ does not refresh. | Fixed in 6.0 release | 1. Open a patient 2. Generate a document that is flagged for the PAQ 3. Open the PAQ 4. Notice the document is not there. 5. Use the Norton button and select refresh, the document now appears. | El Rio CHC
KI90724 | Problem: The Visits section on the My Chart page is not being populated when PHR is generated via the PHR Partial Load Processor. | Known Issue Closed. Fixed and Released in Portal Release: 2.6 | 1) Access a patient’s chart. 2) Create a new encounter and add a procedure. (Procedure code must be in the range of 99200 and 99607). 3) Lock the encounter so PHR gets generated via the PHR Partial Load. 4) Note that the PHR generates and the procedure is present in the CCDA document; however, it is not present on the My Chart page. When requesting PHR manually, the visits section will be populated. | Heartland CHN
N/A | N/A | Per Robin on this case: "This was not a KI, however, it was change to fields in a table to add additional enrollment types, which caused problems for those clients who utilize bulk enrollment. This was not noted in the release notes, and was a part of the scripts run during the upgrade to Spring release 2018." | We have 50,000 patients stuck in a Pending Auto Enrollment status (64). This status is problematic because it does not allow modifications. We are unable to email invitation, generate token or un-enroll. | NA
KI197404 | The Practice Preference General option “Set process date for encounter rate SIM..” does not work for secondary Payers. | Target Patch Release 2/8/2022 | 1. Log into PM 2. Go to Admin-Preferences-Practice -General Tab 3. Under option ‘Set Process Date for Encounter Rate Sim and Encounter Rate Adjustments as’ select setting ‘First charge line Process date or Minimum Process Date, whichever is later’ and click OK to save changes 4. Find an encounter that has charges with process date older than the current date, two payers attached to it and the secondary payer has an encounter rate library attached with the option for the ER sim inserting in charge entry 5. Add transactions to encounter under primary payer and settle balances to the secondary payer 6. Post the batch 7. Bill out secondary encounter rate payer and encounter rate SIM inserts onto charge entry screen but the process date is the current date. | Shasta Community

## Delivered Ideas
ID | Title | Idea Body | Status | Created Date | Full Name | Account Name
IDEA-2491 | Add column to global search results to show whether I have voted on the idea | NACHC - Currently the only way to search previously-submitted ideas is via the global search. When doing a global search, the Ideas grid includes the idea?s title, body/description, number of comments, etc. There is no indication as to whether I have voted on the idea already or not. I have to open each idea, one by one, to see this. This enhancement is to add a column to show my voting status for each Idea in the list of Ideas that are returned after a global search. Or, even better, would be to add the Promote & Demote buttons to the global search results. NACHC | Delivered | 2016-11-11 | Cordt Byrne | One World Community Health Centers, Inc | 130
IDEA-9391 | Add eligibility reason and funding source as options to make required when completing vaccine administration | In 5.9.0 neither VFC eligibility reason nor funding source are available to be made required when completing vaccine administration via File Maint -> Pract Pref -> Orders Module -> Mandatory Data Points. The state of Nebraska requires that all new immunizations include eligibility code and funding source. Please add eligibility reason and funding source as options to make required when completing vaccine administration. #NACHC Please consider promoting these ideas: IDEA-2488 - Release Immunization Module Vaccine Schedule Updates Independent of Application Version Upgrades IDEA-2417 - Multiple Vaccine Stocks and the ability to configure billing IDEA-5787 - Vaccines For Adult (VFA) IDEA-1726 - VFA process (Vaccine for Adults/317 Fund) | Delivered | 2019-01-24 | Cordt Byrne | One World Community Health Centers, Inc | 140
IDEA-4983 | Add Program Name field to Behavioral Health Transfer/Discharge tab template | NACHC - The Screeening/Admit tab in the Behavioral Health KBM has a field to indicate a program name for the program the patient is admitted to. When you discharge or transfer a patient, you cannot specify which program they are being discharged or transferred from. It would be much easier to manage caseloads if there was comparable program name field as on both templates. #NACHC | Delivered | 2017-07-28 | Richard Clarkson | Callen-Lorde Community Health Center | 90
IDEA-2539 | Annual Care Guideline Date not 12 months | NACHC - When we set up an annual protocol for care guidelines - such as reviewing smoking history which is required to be done annually, it should be based upon a calendar year. Currently when you set it up yearly, it doesn't come due until 365 days from last time it was done. If a patient is screened in December, 2015 - they could be seen several times the first 11 months of 2016, and it would not show due. Unless the patient comes in the last month, you could potentially not screen the person in 2016 as the guidelines do not show as due. This can be a compliance issue for several programs. Their should be an option for protocols to be done yearly (365 days) or annually (becomes due January 1st of the following year). FQHC / CHC / NACHC | Delivered | 2016-11-17 | Alan Wegener | Southwest Community Health Center. Inc. | 580
IDEA-11009 | AUC Score Wizard - Allow Alternate CPT Score Selection from Template | When running the AUC Score Wizard from the orders module, providers can select an alternative test if their original order wasn't the highest scoring option. This functionality is not available when launching the AUC Score Wizard from a template. When coming from a template, providers can see that other order choices are more appropriate, but providers cannot select these alternative tests. This IDEA is to allow the provider to change their order, i.e. select an alternative test/order/CPT code, when accessing the AUC Score Wizard from a template. If NextGen doesn't want to turn on this capabaility across the board, then please add an input parameter to the Radiology CDS template trigger to enable/disable this functionality so we can enable it on our custom templates. Without this IDEA, providers are forced to jump through so many unnecessary clicks to change their order based on the AUC score results. NACHC | Delivered | 2019-11-22 | Cordt Byrne | One World Community Health Centers, Inc | 380
IDEA-2834 | Behavioral Health Treatment Plan: | NACHC - The current Behavioral Health Treatment Plan is cumbersome to use, doesn't work well when patients are re-admitted for care, and take too much time for a provider to document what should be a simple to use template. Additionally, the document generated is not easy for the patient to take home and understand. This can lead to patient non-compliance because they cannot simply understand and follow the document as it is printed out of NextGen. Many times it also fails to meet different regulatory bodies or causes frustration for a reviewer when trying to review the patients chart for compliance with care and regulations. The current process impacts providers? productivity, as it just takes way too long to properly document a full treatment plan. A major step in NextGen demonstrating their commitment to the Behavioral Health content would be to rework the treatment plan and document. This one step would be embraced by all NextGen users that have Behavioral Health content. A good treatment plan design, would include controls via a system/practice template which would allow you to turn on/off different settings to meet agency and regulatory needs. For example, some states/regulatory bodies require each problem identified in the assessment to be associated with goals, objectives and interventions in the treatment plan (a golden thread). Some states require signatures by not just the patient and writer but multiple staff and a MD. These types of setting could be controlled through a sys/practice template which would clean up the treatment plan template for the providers. Additionally, creating functionality to end the active goals when they are discharged, would prevent problems months or years later when they came back to treatment (where now they would carry forward with potentially inaccurate data which proves difficult to remove/undo) NACHC FQHC | Delivered | 2017-01-06 | Alan Wegener | Southwest Community Health Center. Inc. | 320
IDEA-0352 | Care Guidelines 1.0 lab results | NACHC - the New care Guidelines 1.0 should include the last lab vaule or at least flag abnormal values so that a provider doesn't have to go into the orders module to know what the outcome of these tests are. FQHC / CHC / NACHC | Delivered | 2016-03-14 | Alan Wegener | Southwest Community Health Center. Inc. | 320
IDEA-2881 | Care Guidelines Alternative Tests | NACHC - Currently the periodicity of the care guidelines is set at the guideline. We need the periodicity to be set at the test or alternative test level because many tests will suffice one guideline and sometimes the test have different periodicities for said guideline. The best example is Colorectal Cancer Screening. The USPSTF recommends screening for colorectal cancer using fecal occult blood testing, sigmoidoscopy, or colonoscopy in adults, beginning at age 50 years and continuing until age 75 years. The risks and benefits of these screening methods vary. Tests that find polyps and cancer Flexible sigmoidoscopy every 5 years* Colonoscopy every 10 years Double-contrast barium enema every 5 years* CT colonography (virtual colonoscopy) every 5 years* Tests that mainly find cancer Guaiac-based fecal occult blood test (gFOBT) every year* , ** Fecal immunochemical test (FIT) every year* , ** Stool DNA test every 3 years* http://www.cancer.org/cancer/colonandrectumcancer/moreinformation/colonandrectumcancerearlydetection/colorectal-cancer-early-detection-acs-recommendations https://www.uspreventiveservicestaskforce.org/Page/Document/UpdateSummaryFinal/colorectal-cancer-screening NACHC | Delivered | 2017-01-13 | Sean Folweiler | Utd Health Ctr of San Joaquin Valley dba Central Valley Collaborative | 300
IDEA-6947 | NG Compendium Updates Excel Workbooks - #NACHC | NACHC - It would be nice to be able to optain copies of the excel workbooks downloaded in the orders management console process without having to go though the orders management console process against a test environmnent. | Delivered | 2018-02-21 | Sean Folweiler | Valley Health Team | 0
IDEA-11926 | OTTO Encounter Creation | The enocunter being created when the patient joins the session creates a very difficult workflow. We would perfer to have the option by practice and by event type to not create the enocunter when the patient joins the visit. When this is turned off the staff would create the encouter manually like face to face encounters. #NACHC | Delivered | 2020-07-13 | Sean Folweiler | Valley Health Team | 60
IDEA-8234 | Patient Care Team Members Documentation with goal to lessen burden of duplicate documentation | #NACHC Currently in 5.9 there are two areas you can add care team member information. The pre-existing location is in Patient Demographics Patient/Provider Relationship. This area allows you to enter if the patient is co-managed and provides access to file maintenance provider file to selet available entries or free text. The new area within the Care Team Members, does allow you to add an pick list item for support role to indicate "co-managed", but it does not prompt file maintenance provider file for ease of entry. End user would need to free text all corresponding information. Requesting new template provide access to file maintenance provider file for ease of entry and eliminate duplicate documentation between these two areas. | Delivered | 2018-07-31 | Rebecca Rudd | Ohio Shared Information Svcs | 150
IDEA-1078 | Patient Portal: Add ability to use an Online Profile by default when sending Portal messages to patients | NACHC - The Patient Portal currently has the ability to send messages under an Online Profile. However users must manually select the Online Profile on each and every message. This Idea is to allow users to set a default Online Profile so when they compose a message the "From" field would default to their preferred online profile. This would apply to both new outgoing messages as well as replies. And if the new preference/setting is blank, then the behavior would match current behavior, i.e. the message would be sent under the user's name. Sourced by NACHC | Delivered | 2016-06-17 | Cordt Byrne | One World Community Health Centers, Inc | 430
IDEA-2420 | Practice Management Demographics Remove Add on Fly | NACHC - In the practice management system there is no way to restrict end users from adding new values to the zipcode, county, country, address type fields. We should be able to have a security preference to restrict access to these fields and the end users should only be able to select the value from a pick list. This is a very important issue for practices submitting UDS reports to the federal government. One of the tables that needs to be reported is Zipcode and there are many invalide zip codes due to manually entry errors. NACHC IDEA | Delivered | 2016-10-27 | Sean Folweiler | Utd Health Ctr of San Joaquin Valley dba Central Valley Collaborative | 900
IDEA-11091 | PRAPARE 5.9.3 Won't let you skip questions to Calculate Score | #NACHC. The newest release of PRAPARE within the ACE (KBM) in 5.9.3 will not allow end users to skip questions to calculate score. Calculate button will remain greyed out until all questions have a reply indicated. Prior versions did not require end user to complete all fields, especially if they were not asked and/or doing a phase approach to implementing PRAPARE. Would like functionality to calculate score based upon completed items on template. | Delivered | 2019-12-17 | Rebecca Rudd | Ohio Shared Information Svcs | 210
IDEA-2086 | Social Determinants of Health / PRAPARE | NACHC - Please investigate adding the collection of Social Determinants of Health to the NG KBM. NACHC has already done a lot of work developing a program around this called PRAPARE. There is information on their website - http://nachc.org/research-and-data/prapare/ Being able to collect this information from within the KBM would be very helpful to our Community Health Centers. ==================================================================================================================== MESSAGE FROM PRODUCT MANAGEMENT: The NACHC PRAPARE template developed by Professional Consulting Service was delivered to the NACHC on 12.22.16. It is a stand-alone release available for NACHC members to download. To access these templates, members are being directed to the NACHC website. | Delivered | 2016-09-16 | Heidi Gerner | Ohio Shared Information Svcs | 110